## Slide 1
ETP RETROFIT PROJECT
WEEKLY REPORT
Tuesday, 12 March 2024

## Slide 2: First half ACTIVITIES CHART
PROJECT NAME | FINISH | BEGIN
Dev Code Merging First Set | 09-02-24 | 01-02-24
Actuals | 09-02-24 | 04-02-24
Environment Setup | 02-02-24 | 01-02-24
Actuals | 05-02-24 | 04-02-24
stock order type | 02-02-24 | 01-02-24
Actuals | 06-02-24 | 05-02-24
communication provider | 02-02-24 | 01-02-24
Actuals | 06-02-24 | 05-02-24
communication template | 05-02-24 | 04-02-24
Actuals | 07-02-24 | 06-02-24
node to node relation | 05-02-24 | 04-02-24
Actuals | 07-02-24 | 06-02-24
stock transfer | 09-02-24 | 05-02-24
Actuals | 09-02-24 | 06-02-24
digital receipt setup | 09-02-24 | 05-02-24
Actuals | 09-02-24 | 06-02-24
upload download history | 09-02-24 | 05-02-24
Actuals | 09-02-24 | 06-02-24
First Set Testing | 16-02-24 | 11-02-24
Actuals | 16-02-24 | 11-02-24
stock order type | 12-02-24 | 11-02-24
Actuals | 12-02-24 | 11-02-24
communication provider | 12-02-24 | 11-02-24
Actuals | 12-02-24 | 11-02-24
communication template | 13-02-24 | 12-02-24
Actuals | 13-02-24 | 12-02-24
node to node relation | 13-02-24 | 12-02-24
Actuals | 13-02-24 | 12-02-24
stock transfer | 15-02-24 | 13-02-24
Actuals | 15-02-24 | 13-02-24
digital receipt setup | 16-02-24 | 14-02-24
Actuals | 16-02-24 | 14-02-24
upload download history | 16-02-24 | 14-02-24
Actuals | 16-02-24 | 14-02-24
Chart: 
| Dev Code Merging First Set | Actuals | Environment Setup | Actuals | stock order type | Actuals | communication provider | Actuals | communication template | Actuals | node to node relation | Actuals | stock transfer | Actuals | digital receipt setup | Actuals | upload download history | Actuals | First Set Unit & Integration Testing | Actuals | stock order type | Actuals | communication provider | Actuals | communication template | Actuals | node to node relation | Actuals | stock transfer | Actuals | digital receipt setup | Actuals | upload download history | Actuals
FINISH | 45331 | 45331 | 45324 | 45327 | 45324 | 45328 | 45324 | 45328 | 45327 | 45329 | 45327 | 45329 | 45331 | 45331 | 45331 | 45331 | 45331 | 45331 | 45338 | 45338 | 45334 | 45334 | 45334 | 45334 | 45335 | 45335 | 45335 | 45335 | 45337 | 45337 | 45338 | 45338 | 45338 | 45338
BEGIN | 45323 | 45326 | 45323 | 45326 | 45323 | 45327 | 45323 | 45327 | 45326 | 45328 | 45326 | 45328 | 45327 | 45328 | 45327 | 45328 | 45327 | 45328 | 45333 | 45333 | 45333 | 45333 | 45333 | 45333 | 45334 | 45334 | 45334 | 45334 | 45335 | 45335 | 45336 | 45336 | 45336 | 45336

## Slide 3: Second Half ACTIVITIES CHART
PROJECT NAME | FINISH | BEGIN
Dev Code Bug fixing First Set | 21-02-24 | 19-02-24
Actuals | 24-02-24 | 19-02-24
Dev Code Merging Second Set | 23-02-24 | 19-02-24
Actuals | 24-02-24 | 19-02-24
stock take | 20-02-24 | 19-02-24
Actuals | 20-02-24 | 19-02-24
Customer List | 20-02-24 | 19-02-24
Actuals | 24-02-24 | 19-02-24
purchase order receive | 22-02-24 | 20-02-24
Actuals | 22-02-24 | 20-02-24
clientelling | 23-02-24 | 21-02-24
Actuals | 24-02-24 | 21-02-24
Second Set Unit, Integration Testing and Bug Fixing | 29-02-24 | 25-02-24
Actuals | 01-03-24 | 25-02-24
stock take | 26-02-24 | 25-02-24
Actuals | 26-02-24 | 25-02-24
Customer List | 27-02-24 | 26-02-24
Actuals | 27-02-24 | 26-02-24
purchase order receive | 28-02-24 | 27-02-24
Actuals | 01-03-24 | 27-02-24
clientelling | 29-02-24 | 28-02-24
Actuals | 01-03-24 | 28-02-24
Impl Merging, Integration Testing | 06-03-24 | 29-02-24
Actuals | 11-03-24 | 29-02-24
UAT | 11-03-24 | 06-03-24
Actuals |  | 
Support | 14-03-24 | 11-03-24
Actuals |  | 
Chart: 
| Dev Code Bug fixing First Set | Actuals | Dev Code Merging Second Set | Actuals | stock take | Actuals | Customer List | Actuals | purchase order receive | Actuals | clientelling | Actuals | Second Set Unit, Integration Testing and Bug Fixing | Actuals | stock take | Actuals | Customer List | Actuals | purchase order receive | Actuals | clientelling | Actuals | Impl Merging, Integration Testing | Actuals | UAT | Actuals | Support | Actuals
FINISH | 45343 | 45346 | 45345 | 45346 | 45342 | 45342 | 45342 | 45346 | 45344 | 45344 | 45345 | 45346 | 45351 | 45352 | 45348 | 45348 | 45349 | 45349 | 45350 | 45352 | 45351 | 45352 | 45357 | 45362 | 45362 | 45365
BEGIN | 45341 | 45341 | 45341 | 45341 | 45341 | 45341 | 45341 | 45341 | 45342 | 45342 | 45343 | 45343 | 45347 | 45347 | 45347 | 45347 | 45348 | 45348 | 45349 | 45349 | 45350 | 45350 | 45351 | 45351 | 45357 | 45362

## Slide 4: Current Status
Over All | Budget | Scope | Resources | Timeline | Quality | Risks
ON
ON
OVER
Access Grand
Environment Setup
First Half Code Merge and Integration
Second Half Code Merge and Integration
IMPL Env Merging
UAT and Support
CURRENT TIMELINE POSITION
08/Mar/2024
RISKS AND ROADBLOCK 1
Access Delayed by 2 days
Port Exposure delayed by 1 day
Build Script
Jenkin Access yet to be provided
Due to build delay QA activities not started
RISKS AND ROADBLOCK 4
Database changes yet to be reflected which had delayed for 3 days even though we initiated 2 days before when we need.
Also web services changes are not reflecting from 06/mar/2024.
PROJECT START DATE
01/Feb/2024
PROJECT END DATE
14/Mar/2024
Might be delayed by 3 working days
Expected : 20/mar/2024
RISKS AND ROADBLOCK 2
Angular UI build was failed on 2 days delayed testing
Changes checked in and Action ID mapping not reflecting on 23 Feb 2023
RISKS AND ROADBLOCK 3
IMPL or Test environment yet to be finalized
OVER
OVER
OVER
OVER

## Slide 5: HIGHLIGHTS AND TAKE AWAYS
  Support from Kiran, Priya, Mansi, Nishita and Shashi
  WhatsApp communication
Things that worked well
  Database changes to start IMPL merging has delayed by 3 days which is affecting our entire budget and timeline.
Things that we collectively need to improve
  Database changes to IMPL environment
  Inventory Sync in IMPL environment
Points that need immediate action

## Slide 6
niranjana.m@ideastoimpacts.com
www.ideastoimpacts.com
020-6719-0000
THANK YOU
Ideas to Impacts Innovations Pvt Ltd
Pallod Farms 3, Baner, Pune 411045
Maharashtra, India